## Sheet1
0 | Issue/Bug | Status | AssignedTo | Comments
1 | Delete an application node and save the config with no nodes. Open the file with no nodes, you get a runtime exceptione… | Closed | Suchi
2 | Requirement: Mark Apps/Screens/Control level nodes from Control explorer and copy to control editor | Closed | Suchi
3 | opening more than one tab with same file name causes app to crash | Closed | Suchi
4 | In ImageCapture mode, ApplicationLocalPath, Type, browser name, browser version, should be added to Atr. | Closed | Suchi
5 | Open 2 image based ATR , update properties of one ATR, properties of other ATR will also get updated. | Open | Raghavan
6 | For Application node, Click of add button should be mandatory before click of save button | Open | Suchi
7 | Issue in multi tab editing when multiple image and automation models are opened | InProgress | Suchi | Need to test again
8 | Requirement: Validations to fit nodes in proper location within Control explorer | InProgress | Suchi
9 | On change of tab, properties grid does not update | Closed | Suchi
10 | Screen capture issues causing app to crash and multiple saves | Open | Raghavan
11 | Post changes to application node – adding name type browser etc the ui is a little skewed | Open | Raghavan
12 | Phython script generation not working | Open | Suchi